## RETROSPECTIVE
SPRINT RETROSPECTIVE
SPRINT ID | START | STOP | KEEP | MORE | LESS
SP000 | Reach out to teammates to understand unity and Git | Shying from reaching out to others or any delay in responses. | Standup calls and in person meetings | Communicate more with teammates | Not communicating in terms of confusion on task assigned and project
SP001 | Push to Git as soon as work is completed, Start tagging people over teams immediately incase of blockers | Not reporting updates | Sprint planning revision during standups | Share useful resources | Not reporting blockers, less of tutorials
SP002 | Share update on trello, teams and Git ASAP | No more tutorials are needed. Any help needed reach out to teammates. | Re-evaluate division of work during standups | Positive comments and appreaciations for team members | Less of rework.
SP003 | Write description for all Git branch, assign story points to tasks before starting work | No more changes to design and assets now | Inprompt meetings and standup calls | Appreciation and encouragement, flag when no work is assigned, merging branches to main branch only after testing is completed, support when working out of strength areas | Creating many branches
Note on C8: stakeholdermap.com: What the team will start doing.
Note on D8: stakeholdermap.com: What the team will stop doing.
Note on E8: stakeholdermap.com: Actions the team will keep doing.
Note on F8: stakeholdermap.com: Actions that need to be done more often.
Note on G8: stakeholdermap.com: Actions that the team will do less of in the next sprint.