## MOMs
Date | Day | Meeting | Duration | MOMs | Members present | Comments/ Feedback
21st Feb | Tuesday | Standup | 20 mins | Disscussed: - Work progress - Blocker or help needed: Struggle with Unity - Reviewed lesson video Actions: - Improvements: reduce text as per feedback in the video - Scheduled in person meeting to help each other with unity | Zong Wang Deonte Allen Gooden Rayman Parmar Sowrabhi Ravi Pallavi Raut | Share work or blockers in advance Set agenda if covering more than standup update
22nd Feb | Wednesday | Inperson work session |  | Worked on static designs on Figma | Sowrabhi, Pallavi, Zong, Deonte
27th Feb | Monday | Tutorial session + Standup |  | Rayman presented tutorial on how to use unity, create panels Discussed work progress Revised sprint plan as per suggestions | Zong Wang Deonte Allen Gooden Rayman Parmar Sowrabhi Ravi Pallavi Raut
1st March | Wednesday | Paried programing session | 7 hrs | Quiz scene, Design and lesson scene | Sowrabhi, Pallavi, Zong
7th March | Tuesday | Standup | 35 minutes | 1. Discussed a couple of bugs on the quiz scene 2. Discussed everyone's work for the week (Sowrabhi, Rayman - Testing, Pallavi - Splash screen, Zong - Burnt down chart, sprint retrospective, Deonte - Complete integration) | Sowrabhi, Pallavi, Zong, Deonte